## Sheet1
DigitalSTROM |  |  |  |  | Software pre-delivery test
Date: |  | 2013-05-17
Revision: |  | 630bfd091d1559b28a84538c4a5fb463e769a04e |  |  | Project | md-configurator
Version: |  | 2.0.1 |  |  | Company: | mobile2DS
Contact: |  | Gregor
Testing environment
Test summary |  |  |  |  | dSS | s2013.09test01
Result |  | Count |  |  | Operating system | Ubuntu ver. 12.04
Result OK |  | 6 |  |  | Browser | Firefox ver. 19.0.2
Result NOK |  | 1 |  |  | Additional tools | mcp ver. 1.0.2-r1
Not tested |  | 0
ID | Priority | Description | REQ ID | Precondition | Actions | Expected result | Expected result UI (screenshot) | Real result | Follow up if NOTOK
1 | 1 | Install the MD application |  | dSS is running and computer is connected over the ethernet | 1.) Change the dSS tab to the Add-ons 2.) In the Install combobox select item MD app 3.) Click OK to install the MD app | MD app icon is visible in the dSS |  | OK | Files copies by hand
2 | 1 | Add first, new MD device using standard input mode |  | New MD device is being added to the room containing only one light and no other dS devices. Scene responder does not have any entries for this new MD device. MD app does not yet have any custom defined actions and/or activities. MD app is started. | 1.) In the tab "Devices" edit the selected device and set following values: - Field "Name" to "first MD device_<dSid>" - Check "Config as MD" - Select proper room - Leave input mode as standard 3.) Press Save button | Device parameters are changed to: - Name contains "first MD device_<dSid> - The selected room is displayed - Sensor function has value "MD motion detector" - Input mode is set to standard In the Scene responder list must be two entries a "switch on" activity and a "switch off" activity |  | NOTOK | - In "Device configurator" Input mode does display current mode - F5 key pressed for page refresh - SR not created when use GIT version, but with the zip its working - maybe cause no execute attributs for files md-config.js and md-shared-js
3 | 1 | Remove one MD device |  | Only one MD device is in the room (possible the first, newly added MD device) | 1.) Start MD app 2.) Edit the selected device in the device list and only uncheck "Config as MD" 3.) Press Save button | The device parameter "Sensor Function" is changed to the "App mode" In the Scene responder list no entry for this MD device should appear |  | OK
4 | 1 | Add first, new MD device using invert input mode |  | New MD device is being added to the room containing only one light and no other dS devices. Scene responder does not have any entries for this new MD device. MD app does not yet have any custom defined actions and/or activities. MD app is started. | 1.) In the tab "Devices" edit the selected device and set following values: - Field "Name" to "first MD device_<dSid>" - Check "Config as MD" - Select proper room - Set input mode as inverted 2.) Press Save button | Device parameters are changed to: - Name contains "first MD device_<dSid> - The selected room is displayed - Sensor function has value "MD motion detector" - Input mode is set to Inverted In the Scene responder list must be two entries a "switch on" activity and a "switch off" activity |  | OK
5 | 1 | Change MD device input mode |  | New MD device already added to the room containing only one light and no other dS devices. Scene responder has two entries (on/off) for this new MD device using input mode standard. MD app does not yet have any custom defined actions and/or activities. MD app is started. | 1.) In the tab "Devices" edit the selected device and set following values: - Change input mode as inverted 2.) Press Save button | Only device parameter Input mode is changed to Inverted In the Scene responder list must be two entries a "switch on" activity and a "switch off" activity, but with reverse functionality |  | OK
6 | 1 | Use case 1 |  | In the room there is on light and one MD set as MD Motion detector using input mode standard. SR has two entries for it, on entry and off entry. No other conditions are set and no motion is detected and light is off. | 1.) Between each action wait around 10 seconds and UI actions are not covered with this test. 2.) Simulate motion (use special switch, python scripts) 3.) Simulate no motion (use special switch, python scripts) 4.) Simulate motion (use special switch, python scripts) 5.) Simulate no motion (use special switch, python scripts) | On each motion event a light should turn on and on each no motion event a light should turn off. |  | OK | Sometimes it takes even longer than 10 sec to turn the light on/off.
7 | 1 | Use case 1 using Inverted Input mode |  | In the room there is on light and one MD set as MD Motion detector using input mode standard. SR has two entries for it, on entry and off entry. No other conditions are set and no motion is detected and light is off. | 1.) Between each action wait around 10 seconds and UI actions are not covered with this test 2.) Simulate motion (use special switch, python scripts) 3.) Simulate no motion (use special switch, python scripts) 4.) Repeat steps 2.) and 3.) once more 5.) With UI Device configurator change input mode to Inverted 6.) Simulate motion (use special switch, python scripts) 7.) Simulate no motion (use special switch, python scripts) 8.) Repeat steps 6.) and 7.) once more | When using the input mode Standard the light should turn ON on each motion event and turn OFF on each no motion event. When input mode is changed to the Inverted mode then light should turn ON on each no motion event and turn OFF on oeach motion event. |  | OK | Sometimes it takes even longer than 10 sec to turn the light on/off.
8 | 1 | [6 empty] | NOTTESTED
9 | 1 | [6 empty] | NOTTESTED